## Sheet1
Subcontractor: | B R contractor
State: | Uttar Pradesh |  | M/s B R contractor |  |  |  |  | Pipe Laying work
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Aadhar card recovery hold Amount | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 10% | 10% | 18% | [6 empty] | 1% | 5%
55358
55358 | Chourawala Village Pipe laying work | 2023-03-01 | 1 | 327550 | 0 | 327550 | 58959 | 386509 | 3276 | 16378 | 32755 | 32755 | 58959 | 205422 |  | 36964 | 4.10.23 | RIUP22/2552 | 36964 | 0 |  |  | 36964 | 13-03-2023 NEFT/AXISP00370901259/RIUP22/2552/B R CONTRACTOR 36964.00
55358 | Chourawala Village Pipe laying work | 2023-04-17 | 1 | 399713.45 | 0 | 399713.45 | 71948 | 471661.45 | 3997 | 19986 | 39971 | 39971 | 71948 | 0 |  | 295788 |  | RIUP22/2578 | 200000 | 2000 | 0 | 0 | 198000 | 14-03-2023 NEFT/AXISP00371329489/RIUP22/2578/B R CONTRACTOR 198000.00
55358 | Chourawala Village Pipe laying work | 2023-07-26 | 2 | 479885 |  | 479885 | 86379 | 566264 | 4799 | 23994 | 23994 | 47989 | 86379 |  | 6400 | 372709 |  | SPUP23/0205 | 150000 | 1500 | 0 | 0 | 148500 | 20-04-2023 20-04-2023 NEFT/AXISP00383281368/SPUP23/0205/B R CONTRACTOR 148500.00
55358 | Chourawala Village Pipe laying work | 2023-10-30 | 3 | 352115 |  | 352115 | 63381 | 415496 | 3521 | 17606 | 35212 | 35212 | 63381 | 9308 |  | 251256 |  | RIUP23/223 | 100000 | 1000 | 0 | 0 | 99000 | 12-05-2023 NEFT/AXISP00389894136/RIUP23/223/B R CONTRACTOR 99000.00
55358 | [17 empty] | RIUP23/548 | 59400 | 0 | 0 | 0 | 59400 | 06-06-2023 NEFT/AXISP00396045005/RIUP23/548/B R CONTRACTOR 59400.00
55358 | [17 empty] | RIUP23/923 | 100000 | 1000 | 0 | 0 | 99000 | 28-06-2023 NEFT/AXISP00401332299/RIUP23/923/B R CONTRACTOR 99000.00
55358 | [17 empty] | RIUP23/2391 | 135000 | 1350 | 0 | 0 | 133650 | 30-09-2023 NEFT/AXISP00428978262/RIUP23/2391/B R CONTRACTOR/ICIC00MUZAF 133650.00
55358 | [17 empty] | RIUP23/3104 | 182203 | 1822.03 | 0 | 0 | 182203 | 08-11-2023 NEFT/AXISP00441869064/RIUP23/3104/B R CONTRACTOR/ICIC00MUZAF 182203.00
55358 | [17 empty] | RIUP23/3751 | 69300 | 693 |  |  | 69300 | 14-12-2023 NEFT/AXISP00487432569/RIUP23/3751/B R CONTRACTOR/ICIC00MUZAF 69300.00
55358
[15 empty] | Total Payable Amount Rs. - | 956717 |  |  |  | Total Paid Amount Rs. - |  |  | 1026017
|  |  |  | 1559263.45 | 0 | 1559263.45 | 280667 | 1839930.45 | 15593 | 77964 | 131932 | 155927 | 280667 | 214730 | [5 empty] | Balance Payable Amount Rs. - |  |  | -69300
M/s B R contractor
[11 empty] | Total Hold ( SD+OC+HT ) |  | 365823
[11 empty] | DPR Excess Hold |  | 214730
[11 empty] | Advance / Surplus |  | -69300
Debit
[11 empty] | GST Remaining |  | 280667