## Sheet1
Subcontractor: | Ankita Infratech
State: | Uttar Pradesh |  | M/s Ankita Infratech |  |  |  | Pipeline Laying work
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount |  | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10%
54577
54577 | SIKHREDA JAMALPUR BANGAR village Pipe Line Work at Village-SIKHREDA JAMALPUR BANGAR | 2023-03-10 | 8 | 419330.68 | 15734 | 403596.68 | 72647 | 476243.68 | 4035.9668 | 20179.834 | 40359.668 | 40359.668 | 72647 | 52217 | 246445 |  | 247500 | 30-01-2023 NEFT/AXISP00358212247/RIUP22/2045/ANKITA INFRATEC ₹ 2,47,500.00
54577 | SIKHREDA JAMALPUR BANGAR Village Pipe Line Work at Village-SIKHREDA JAMALPUR BANGAR | 2023-07-12 | 9 or 20 | 548384 | 15734 | 532650 | 95877 | 628527 | 5326.5 | 26632.5 | 53265 | 53265 | 95877 | 22081 | 372080 |  | 99000 | 18-03-2023 NEFT/AXISP00372424203/RIUP22/2664/ANKITA INFRATEC 99000.00
54577 | GST |  | 8 | 72647 | [10 empty] | 72647 |  | 272023 | 08-08-2023 NEFT/AXISP00413896720/RIUP23/1098/ANKITA INFRATEC 272023.00
54577 | GST |  | 20 | 95877 | [10 empty] | 95877 |  | 72647 | 02-11-2023 NEFT/AXISP00439799508/RIUP23/3041/ANKITA INFRATECH/BARB0BARHXX 72647.00
[17 empty] | 95877 | 08-11-2023 NEFT/AXISP00441999422/RIUP23/3042/ANKITA INFRATECH/BARB0BARHXX 95877.00
[16 empty] | 54389 | 0 |  | 2
54389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 148500 | 21-01-2023 NEFT/AXISP00356449518/RIUP22/1933/ANKITA INFRATEC ₹ 1,48,500.00
[16 empty] | 53706 |  |  | -148500
53706 | Sadpur Village Pipeline laying work | 2023-03-10 | 7 | 738716 | 11539 | 727177 | 130891.86 | 858068.86 | 7271.77 | 36358.85 | 72717.7 | 72717.7 | 130891.86 | 52356 | 485755 |  | 247500 | 15-12-2022 NEFT/AXISP00346453824/RIUP22/1526/ANKITA INFRATEC 247500.00 | Bill not booked
[17 empty] | 148500 | 08-03-2023 NEFT/AXISP00369766192/RIUP22/2505/ANKITA INFRATEC 148500.00
[16 empty] | 50934 |  |  | 89755
50934 | Tigri Village Boundary Linework | 2023-03-10 | 4 | 502600 |  | 502600 | 90468 | 593068 | 5026 | 25130 |  |  | 90468 | 97468 | 374976 |  | 99000 | 17-06-2022 NEFT/AXISP00296770063/RIUP22/215/ANKITA INFRATECH 99000.00
50934 | GST Release note | 2023-03-11 | 7 | 90468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90468 |  | 247500 | 24-10-2022 NEFT/AXISP00331202727/RIUP22/1107/ANKITA INFRATEC 247500.00
[17 empty] | 28476 | 25-04-2023 25-04-2023 NEFT/AXISP00384260582/SPUP23/0283/ANKITA INFRATECH 28476.00
[17 empty] | 90468 | 02-05-2023 NEFT/AXISP00386545787/SPUP23/0343/ANKITA INFRATECH 90468.00
[16 empty] | 50935 |  |  | 0
50935 | Badh Village Boundary Linework | 2023-03-10 | 7 | 455000 | 0 | 455000 | 81900 | 536900 | 4550 | 22750 | 0 | 0 | 81900 | 41300 | 386400 |  | 99000 | 17-06-2022 NEFT/AXISP00296770064/RIUP22/230/ANKITA INFRATECH 99000.00
50935 | GST Release note | 2023-03-11 | 7 | 81900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81900 |  | 198000 | 01-10-2022 NEFT/AXISP00324596978/RIUP22/875/ANKITA INFRATECH 198000.00
[17 empty] | 89400 | 20-10-2022 NEFT/AXISP00330179779/RIUP22/1017/ANKITA INFRATEC 89400.00
[17 empty] | 81900 | 26-04-2023 26-04-2023 NEFT/AXISP00384417481/SPUP23/0250/ANKITA INFRATECH 81900.00
0
[9 empty] | 26210.2468 | 131051.234 | 166342.468 | 166342.468 | 471783.86 | 265422 | 2206548 |  | 2265291
-58743
M/s Ankita Infratech
[11 empty] | Total Hold ( SD+OC+HT ) |  | 463736.17
[11 empty] | DPR Excess Hold |  | 265422
[11 empty] | Advance / Surplus |  | 0
Debit
[11 empty] | GST Remaining |  | 130891.86