## Sheet1
Subcontractor: | Cricket International
State: | Uttar Pradesh |  | Cricket International |  |  |  |  | Pipe Laying work
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%), Commissioning, Hydro Testing | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 5% | 10% | 18% | [5 empty] | 1% | 20%
57611
57611 | Ahmadwala Village Pipe laying work | 2023-06-17 | 1 | 138993 | 0 | 138993 | 25019 | 164012 | 1389.93 | 6949.65 | 6949.65 | 13899.3 | 25019 | 8189.5 | 101615 | 6.10.23 | RIUP23/871 | 101614 | 0 | 0 | 0 | 101614 | 28-06-2023 NEFT/AXISP00401332289/RIUP23/871/CRICKET INTERNAT 101614.00
57611 | Ahmadwala Village Pipe laying work | 2023-07-27 | 2 | 235651.62 | 0 | 235651.62 | 42417.2916 | 278068.9116 | 2356.5162 | 11782.581 | 11782.581 | 23565.162 | 42417.2916 | 32757.12 | 153408 |  | RIUP23/1270 | 153407 | 0 | 0 | 0 | 153407 | 31-07-2023 NEFT/AXISP00410478616/RIUP23/1270/CRICKET INTERNA ₹ 1,53,407.00
57611 | Ahmadwala Village Pipe laying work | 2023-08-29 | 3 | 202945 |  | 202945 | 36530 | 239475 | 2029.45 | 10147.25 | 10147.25 | 20294.5 | 36530 | 0 | 160327 |  | RIUP23/1821 | 160327 | 0 | 0 | 0 | 160327 | 04-09-2023 NEFT/AXISP00421476869/RIUP23/1821/CRICKET INTERNATIO/ICIC0003872 160327.00
57611 | GST Releae note | 2023-10-04 | 3 | 103966 |  | 103966 |  | 103966 | [6 empty] | 103966 | [6 empty] | 103966 | 26-10-2023 NEFT/AXISP00437006014/RIUP23/2762/CRICKET INTERNATIO/ICIC0003872 103966.00
59349 | Malpura Village Pipe laying work | 2023-09-26 | 1 | 248223 | 0 | 248223 | 0 | 248223 | 2482.23 | 12411.15 | 24822.3 | 24822.3 | 0 | 0 | 183685 | 59349 | RIUP23/2383 | 183685 | 0 | 0 | 0 | 183685 | 30-09-2023 NEFT/AXISP00429071459/RIUP23/2383/CRICKET INTERNATIO/ICIC0003872 183687.00
59349 | GST Release note | 2023-10-04 | 1 | 44680 |  | 44680 |  | 44680 | [6 empty] | 44680 | 28.10.23 |  |  |  | 0 | 0 | 44680 | 01-11-2023 NEFT/AXISP00439457387/RIUP23/2761/CRICKET INTERNATIO/ICIC0003872 44680.00
59349 | Malpura Village Pipe laying work | 2023-10-25 | 5 | 252459.6 | 0 | 252459.6 | 0 | 252459.6 | 2524.596 | 12622.98 | 25245.96 | 25245.96 | 0 | 9553 | 177267 | [6 empty] | 177267 | 01-11-2023 NEFT/AXISP00439227019/RIUP23/3001/CRICKET INTERNATIO/ICIC0003872 177267.00
[13 empty] | Total Payable Amount Rs. - |  | 924948 |  |  |  |  | Total Paid Amount Rs. - |  | 924946
[20 empty] | Balance Payable Amount Rs. - |  | 2