## Sheet1
Subcontractor: | Civil Infra Solutions
State: | Uttar Pradesh |  | Civil Infra Solutions |  |  |  |  | Pipe Laying work
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%), Commissioning, Hydro Testing | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 7.5% | 5% | 5% | 10% | 15% | [5 empty] | 1% | 20%
47517
47517 | Saharanpur village Pipe Laying work | 2020-12-28 | 1 | 700000 |  | 700000 | 126000 | 826000 | 52500 |  |  |  | 105000 |  | 668500 |  | RIUP27 | 1987560 | 0 | 0 | 0 | 1987560 | 28/09/2021 NEFT-N271210774871712-RIUP27-CIVIL INFRASOLUTIONS 271215539587 1,987,560.00
47517 | Saharanpur village Pipe Laying work | 2021-01-14 | 2 | 1433000 |  | 1433000 | 257940 | 1690940 | 107475 |  |  |  | 214950 |  | 1368515
47517 | Saharanpur village Pipe Laying work | 2021-08-19 | 3 | 2208400 |  | 2208400 | 397512 | 2605912 | 165630 |  |  |  | 331260 |  | 2109022
[13 empty] | Total Payable Amount Rs. - |  | 4146037 |  |  |  |  | Total Paid Amount Rs. - |  | 1987560
[20 empty] | Balance Payable Amount Rs. - |  | 2158477
[5 empty] | ITEM | DPR | CUM | EXCESS | RATE | AMT
[5 empty] | BOE | 0 | 163.79 | 163.79 | 50 | 8189.5