## Sheet1
Subcontractor: | Golden Key Construction
State: | Uttar Pradesh |  | Golden Key Construction |  |  |  |  | Pipe Laying work | [7 empty] | 2023-04-26
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | Hold the Amount because the Qty. is more then the DPR | GST_SD_Amount | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR | Advance Village Wise
[7 empty] | 18% |  | 1% | 5% | 5% | 10% |  | 18% |  |  |  |  | 1%
58095
58095 | Siakandarpur Kalan Village Block - Khatauli Pipe laying work | 2023-07-07 | 2 | 371788.38 | 0 | 371788 | 66922 | 438710 | 3718 | 18589 | 18589.4 | 37178.8 | 0 | 66922 | 293713 |  | RIUP23/966 | 150000 | 1500 | 148500 | 30-06-2023 NEFT/AXISP004045214526/RIUP23/966/GOLDEN KEY CON 148500.00 | -376173
58095 | Siakandarpur Kalan Village Pipe laying work | 2003-09-01 | 4 | 1348063 | 13460 | 1334603 | 240229 | 1574832 | 13346 | 66730 | 66730.15 | 133460.3 | 199079 | 240229 | 855258 |  | RIUP23/1075 | 145213 | 0 | 145213 | 14-07-2023 NEFT/AXISP00406995902/RIUP23/1075/GOLDEN KEY CONS 145213.00
58095 | GST |  | 2 | 66922 | [10 empty] | 66922 |  | RIUP23/1889 | 200000 | 2000 | 198000 | 24-07-2023 NEFT/AXISP00408935256/RIUP23/1189/GOLDEN KEY CONS 198000.00
58095 | Siakandarpur Kalan Village Pipe laying work | 2024-01-16 | 17 | 1522088 | 132900 | 1389188 | 250054 | 1639242 | 13892 | 69459 | 138918.8 | 138918.8 | 611836 | 250054 | 416163 |  | RIUP23/1940 | 400000 | 0 | 400000 | 11-09-2023 NEFT/AXISP00423501808/RIUP23/1940/GOLDEN KEY CONSTRU/SBIN0000713 400000.00
58095 | GST |  | 4 | 240229 | [10 empty] | 240229 |  | RIUP23/2826 | 257258 |  | 257258 | 23-10-2023 NEFT/AXISP00436469169/RIUP23/2826/GOLDEN KEY CONSTRU/SBIN0000713 257258.00
58095 | GST |  | 17 | 250054 | [10 empty] | 250054 |  | RIUP23/3226 | 200000 | 2000 | 198000 | 10-11-2023 NEFT/AXISP00443237227/RIUP23/3226/GOLDEN KEY CONSTRU/SBIN0000713 198000.00
58095 | [16 empty] | RIUP23/4006 | 66922 |  | 66922 | 09-01-2024 NEFT/AXISP00460826661/RIUP23/4006/GOLDEN KEY CONSTRU/SBIN0000713 66922.00
58095 | [16 empty] | RIUP23/4374 | 218136 | 0 | 218136 | 09-02-2024 NEFT/AXISP00469899335/RIUP23/4374/GOLDEN KEY CONSTRU/SBIN0000713 218136.00 | Payment difference by Rohit Sir Rs.27
58095 | [16 empty] | RIUP23/4855 | 240229 |  | 240229 | 22-03-2024 NEFT/AXISP00483444822/RIUP23/4855/GOLDEN KEY CONSTRU/SBIN0000713 240229.00
58095 | [16 empty] | RIUP23/5295 | 250054 |  | 250054 | 06-04-2024 NEFT/AXISP00489186683/RIUP23/5295/GOLDEN KEY CONSTRU/SBIN0000713 250054.00
58095 | [19 empty] | 198000 | 29-08-2024 NEFT/AXISP00533195023/RIUP24/1574/GOLDEN KEY CONSTRU/SBIN0000713 198000.00
58095 | [19 empty] | 178200 | 17-09-2024 NEFT/AXISP00541203757/RIUP24/1796/GOLDEN KEY CONSTRU/SBIN0000713 178200.00
[16 empty] | 59006 |  |  | 0
59006 | Chokda Kalan Village Block - Charthawala Pipe laying work | 2023-08-21 | 4 | 1382537.25 | 9460 | 1373077 | 247154 | 1620231 | 13731 | 68654 | 68653.85 | 137307.7 | 55518 | 247154 | 1029212 |  | RIUP23/1940 | 1029212 | 0 | 1029212 | 28-08-2023 NEFT/AXISP00418773002/RIUP23/1715/GOLDEN KEY CONSTRU/SBIN0000713 1029212.00 | -99001
59006 | Chokda Kalan Village Pipe laying work | 2023-10-29 | 8 | 445700 | 7160 | 438540 | 78937 | 517477 | 4385 | 21927 | 43854 | 43854 | 93837 | 78937 | 230683 |  | RIUP23/3102 | 230684 | 0 | 230684 | 08-11-2023 NEFT/AXISP00442118550/RIUP23/3102/GOLDEN KEY CONSTRU/SBIN0000713 230684.00
59006 | Chokda Kalan Village Pipe laying work | 2023-11-10 | 11 | 308000 | 0 | 308000 | 55440 | 363440 | 3080 | 15400 | 30800 | 30800 | 15400 | 55440 | 212520 |  | RIUP23/3103 | 212520 |  | 212520 | 14-12-2023 NEFT/AXISP00452996799/RIUP23/3668/GOLDEN KEY CONSTRU/SBIN0000713 212520.00
59006 | GST |  | 11 | 134377 | [10 empty] | 134377 |  | RIUP23/4027 | 134377 |  | 134377 | 01-02-2024 NEFT/AXISP00467277209/RIUP23/4027/GOLDEN KEY CONSTRU/SBIN0000713 134377.00
59006 | GST |  | 4 | 247154 | [10 empty] | 247154 |  | RIUP23/4854 | 247154 |  | 247154 | 06-03-2024 NEFT/AXISP00477945202/RIUP23/4854/GOLDEN KEY CONSTRU/SBIN0000713 247154.00
59006 | [19 empty] | 99000 | 29-08-2024 NEFT/AXISP00533195024/RIUP24/1575/GOLDEN KEY CONSTRU/SBIN0000713 99000.00
59117
59117 | Mohidddipur Village Block - Khatauli Village Pipe laying work | 2023-09-12 | 6 | 694432.5 | 0 | 694433 | 124998 | 819431 | 6944 | 34722 | 34721.65 | 69443.3 | 80179 | 124998 | 468423 |  | RIUP23/1886 | 100000 | 1000 | 99000 | 07-09-2023 NEFT/AXISP00422654405/RIUP23/1886/GOLDEN KEY CONSTRU/SBIN0000713 99000.00 | -197999
59117 | Mohidddipur Village Pipe laying work | 2023-11-03 | 10 | 365555 | 0 | 365555 | 65800 | 431355 | 3656 | 18278 | 36555.5 | 36555.5 | 259931 | 65800 | 10579 |  | RIUP23/2427 | 369423 | 0 | 369423 | 03-10-2023 NEFT/AXISP00430209791/RIUP23/2427/GOLDEN KEY CONSTRU/SBIN0000713 369423.00
59117 | GST |  | 10 | 65800 | [10 empty] | 65800 |  |  |  |  | 10578 | 09-11-2023 NEFT/AXISP00442790292/RIUP23/3146/GOLDEN KEY CONSTRU/SBIN0000713 10578.00
59117 | GST |  | 6 | 124998 | [10 empty] | 124998 |  |  |  |  | 65800 | 09-01-2024 NEFT/AXISP00460826662/RIUP23/4007/GOLDEN KEY CONSTRU/SBIN0000713 65800.00
59117 | [19 empty] | 124998 | 30-03-2024 NEFT/AXISP00486493284/RIUP23/4856/GOLDEN KEY CONSTRU/SBIN0000713 124998.00
59117 | [19 empty] | 99000 | 29-08-2024 NEFT/AXISP00533195025/RIUP24/1576/GOLDEN KEY CONSTRU/SBIN0000713 99000.00
59117 | [19 empty] | 99000 | 29-08-2024 NEFT/AXISP00533195026/RIUP24/1577/GOLDEN KEY CONSTRU/SBIN0000713 99000.00
57729 | KAMALPUR Village Block - Shahpur Pipeline laying work | 2023-06-07 | 1 | 314345.18 | 0 | 314345 | 56582 | 370927 | 3143 | 15717 | 15717 | 31435 | 71970 | 56582 | 176363 | 57729 | RIUP23/716 | 176363 | 0 | 176363 | 19-06-2023 NEFT/AXISP00399545673/RIUP23/716/GOLDEN KEY CONST 176363.00 | -99000
57729 | GST Release Note | 2023-09-16 | 1 | 56582 | 0 | 56582 | [8 empty] | 56582 |  | RIUP23/2354 | 56582 | 0 | 56582 | 30-09-2023 NEFT/AXISP00429227610/RIUP23/2354/GOLDEN KEY CONSTRU 56582.00
57729 | KAMALPUR Village Pipeline laying work | 2023-06-07 | 7 | 615768 | 12460 | 603308 | 108595 | 711903 | 6033 | 30165 | 60331 | 60331 | 16774 | 108595 | 429674 |  | RIUP23/3103 | 56583 |  | 429675 | 08-11-2023 NEFT/AXISP00442118549/RIUP23/3103/GOLDEN KEY CONSTRU/SBIN0000713 429675.00
57729 | GST Release Note |  | 7 | 108595 | 0 | 108595 | [8 empty] | 108595 |  | RIUP23/3753 | 56584 |  | 198000 | 14-12-2023 NEFT/AXISP00452966709/RIUP23/3753/GOLDEN KEY CONSTRU/SBIN0000713 198000.00
57729 | KAMALPUR Village Pipeline laying work | 2023-12-19 | 12 | 813194 | 75000 | 738194 | 132875 | 871069 | 7382 | 36910 | 73819 | 73819 | 25850 | 132875 | 520414 |  | RIUP23/4035 | 56585 |  | 108596 | 18-01-2024 NEFT/AXISP00463442553/RIUP23/4035/GOLDEN KEY CONSTRU/SBIN0000713 108596.00
57729 | KAMALPUR Village Pipeline laying work | 2024-03-18 | 20 | 1312575 | 0 | 1312575 | 236264 | 1548839 | 13126 | 65629 | 131258 | 131258 | 40343 | 236264 | 930961 |  |  |  |  | 322414 | 09-02-2024 NEFT/AXISP00469899336/RIUP23/4424/GOLDEN KEY CONSTRU/SBIN0000713 322414.00
57729 | GST Release Note |  | 12 | 132875 | [10 empty] | 132875 |  |  |  |  | 297000 | 17-02-2024 NEFT/AXISP00472224389/RIUP23/4749/GOLDEN KEY CONSTRU/SBIN0000713 ₹ 2,97,000.00
57729 | GST |  | 20 | 236264 | [10 empty] | 236264 |  |  |  |  | 500000 | 26-04-2024 NEFT/AXISP00493934368/RIUP24/005/GOLDEN KEY CONSTRU/SBIN0000713 500000.00
57729 | [19 empty] | 132875 | 14-06-2024 NEFT/AXISP00509460934/RIUP23/5124/GOLDEN KEY CONSTRU/SBIN0000713 132875.00
57729 | [19 empty] | 133961 | 14-06-2024 NEFT/AXISP00509460933/RIUP24/0863/GOLDEN KEY CONSTRU/SBIN0000713 133961.00
57729 | [19 empty] | 236262 | 03-08-2024 NEFT/AXISP00524511266/RIUP24/1093/GOLDEN KEY CONSTRU/SBIN0000713 236264.00
57729 | [19 empty] | 99000 | 29-08-2024 NEFT/AXISP00533195026/RIUP24/1577/GOLDEN KEY CONSTRU/SBIN0000713 99000.00
60099
60099 | Muzahidpur village Block Khatauli Pipe Laying work | 2023-11-29 | 9 | 461645 | 8000 | 453645 | 81656 | 535301 | 4536.45 | 22682 | 45364.5 | 45365 | 0 | 81656 | 335697.05 |  | RIUP23/716 | 150000 | 0 | 148500 | 10-11-2023 NEFT/AXISP00443464531/RIUP23/3260/GOLDEN KEY CONSTRU/SBIN0000713 148500.00 | 0.3
60099 | Muzahidpur village Block Khatauli Pipe Laying work | 2024-01-24 | 18 | 133125 | 0 | 133125 | 23963 | 157088 | 1331.25 | 6656 | 13312.5 | 13313 | 0 | 23963 | 98512.25 |  | RIUP23/3669 | 187197 |  | 187197 | 14-12-2023 NEFT/AXISP00452966710/RIUP23/3669/GOLDEN KEY CONSTRU/SBIN0000713 187197.00
60099 | GST Release Note |  | 9 | 81656 | [10 empty] | 81656 |  | RIUP23/4629 | 98512 |  | 98512 | 16-02-2024 NEFT/AXISP00471832018/RIUP23/4629/GOLDEN KEY CONSTRU/SBIN0000713 ₹ 98,512.00
60099 | GST Release Note |  | 18 | 23963 | [10 empty] | 23963 |  |  |  |  | 81656 | 26-04-2024 NEFT/AXISP00494052855/RIUP24/0179/GOLDEN KEY CONSTRU/SBIN0000713 81656.00
60099 | [14 empty] | 0 |  |  |  |  | 23963 | 26-04-2024 NEFT/AXISP00494052856/RIUP23/5123/GOLDEN KEY CONSTRU/SBIN0000713 23963.00
62273
62273 | RASULPUR village PIPE LINE WORK AT RASULPUR | 2024-02-08 | 19 | 434014 | 4000 | 430014 | 77403 | 507417 | 4300.14 | 21501 | 43001.4 | 43001 | 61394 | 77403 | 256816.46 |  | RIUP23/4800 | 150000 | 0 | 256817 | 06-04-2024 NEFT/AXISP00489186662/RIUP23/4800/GOLDEN KEY CONSTRU/SBIN0000713 256817.00 | -0.54
62273 | GST Release Note |  | 19 | 77403 | [10 empty] | 77403 |  | RIUP23/5191 | 187197 |  | 77403 | 06-04-2024 NEFT/AXISP00489186671/RIUP23/5191/GOLDEN KEY CONSTRU/SBIN0000713 77403.00
62273
[9 empty] | 102603.84 | 513019 | 821626.75 | 1026040.4 | 1532111 | 1846872 | 8111860.76 |  | Total Paid Amount Rs. - |  |  | 8884034 |  | -772173.24
[17 empty] | Balance Payable Amount Rs. - |  |  | -772173.24
Golden Key Construction
10.12.2024 - By Nakshatra
[9 empty] | Hold Amount |  | 2360686.15
[9 empty] | Advance / Surplus |  | -772173.24
[9 empty] | GST Remaining |  | 0
[9 empty] | Debit |  | Nil
[9 empty] | DPR Excess Hold |  | 1532111