## Sheet1
Subcontractor: | Gurunanak Engineers
State: | Uttar Pradesh |  | M/S Gurunanak Engineers |  |  | Drilling work
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | SD (5%) | Advance paid | Hold amount for excess qty. against DPR | Total_Amount | UTR | Advance Village Wise
[7 empty] | 18% |  | 1% | 5% | 18% |  |  |  |  | 2% | 5%
56278 | Suketari Village Drilling work | 2023-05-02 | 2 | 269584.5 | 25175 | 244410 | 43994 | 288404 | 2444 | 12221 | 43994 | 0 | 229745 |  |  | 0 | 0 | 0 |  | 229745 | 16-05-2023 IFT/IFT23136007300/RIUP23/251/GURU NANAK ENGINEER 229745.00 | 0
56278 | GST Release Note |  | 2 | 43994 | [8 empty] | 43994 | [6 empty] | 43994 | 02-08-2023 IFT/IFT23214034443/RIUP23/1331/GURU NANAK ENGINEE 43994.00
56278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0
56074 | Kasauli Village Drilling work | 2023-04-06 | 1 | 271392 | 17982 | 253410 | 45614 | 299024 | 2534 | 12671 | 45614 | 0 | 238205 | [6 empty] | 238205 | 19-04-2023 19-04-2023 IFT/IFT23109017141/SPUP23/0154/GURU NANAK ENGINEE 238205.00 | 0
56074 | GST Release Note |  | 1 | 45614 | [8 empty] | 45614 | [6 empty] | 45614 | 02-08-2023 IFT/IFT23214034444/RIUP23/1330/GURU NANAK ENGINEE 45614.00
56074
55549 | Sardhan Village Drilling work | 2023-03-22 | 27 | 268231.5 | 38661 | 229571 | 41323 | 270894 | 2296 | 11479 | 41323 | 0 | 215796 | [6 empty] | 215795 | 29-03-2023 IFT/IFT23088047699/RIUP22/2729/GURU NANAK ENGINEE 215795.00 | 1
55549 | GST Release Note | 2023-04-17 | 27 | 41323 | [8 empty] | 41323 | [6 empty] | 41323 | 21-04-2023 IFT/IFT23111031165/RIUP23/033/GURU NANAK ENGINEER 41323.00
55549
55094 | Shakarpur Village Drilling work | 2023-03-06 | 26 | 270034.5 | 34705 | 235330 | 42359 | 277689 | 2353 | 11767 | 42359 | 0 | 221210 | [6 empty] | 221211 | 15-03-2023 IFT/IFT23074020147/RIUP22/2560/GURU NANAK ENGINEE 221211.00 | -1
| GST Release Note | 2023-04-21 | 26 | 42359 | [8 empty] | 42359 | [6 empty] | 42359 | 21-04-2023 IFT/IFT23111031167/RIUP23/032/GURU NANAK ENGINEER 42359.00
55003 | Malpur village - Drilling work | 2023-02-08 | 25 | 247583 | 45405 | 202178 | 36392.04 | 238570.04 | 2022 | 10109 | 0 | 36392.04 | 190047 | [6 empty] | 89100 | 28-02-2023 IFT/IFT23059052173/RIUP22/2353/GURU NANAK ENGINEE 89100.00 | 0
55003 | GTS Release Note | 2023-04-17 | 25 | 36392 | [8 empty] | 36392 | [6 empty] | 100947 | 02-03-2023 IFT/IFT23061020770/RIUP22/2398/GURU NANAK ENGINEE 100947.00
55003 | [19 empty] | 36392 | 21-04-2023 IFT/IFT23111031166/RIUP23/031/GURU NANAK ENGINEER 36392.00
55003
55002 | Kailanpur Village Drilling work | 2023-02-08 | 24 | 269280 | 44955 | 224325 | 40379 | 264704 | 2243 | 11216 | 40379 | 0 | 210866 | [6 empty] | 99000 | 28-02-2023 IFT/IFT23059052171/RIUP22/2346/GURU NANAK ENGINEE 99000.00 | 1
55002 | GST Release Note | 2023-04-21 | 24 | 40379 | [8 empty] | 40379 | [6 empty] | 111866 | 02-03-2023 IFT/IFT23061020769/RIUP22/2397/GURU NANAK ENGINEE 111866.00
55002 | [19 empty] | 40378 | 21-04-2023 IFT/IFT23111031168/RIUP23/030/GURU NANAK ENGINEER 40378.00
55002
54175 | Bhojaheri Village Drilling work | 2023-01-06 | 20 | 260261.5 | 26073.9 | 234187.6 | 42153.768 | 276341.368 | 2341.876 | 11709.38 | 6600 | 42153.768 | 213536.344 | [6 empty] | 213536 | 18-01-2023 IFT/IFT23018003653/RIUP22/1874/GURU NANAK ENGINEE ₹ 2,13,536.00 | -0.656
54175 | GST Release Note | 2023-02-20 | 20 | 42153 | 0 | 42153 | 0 | 42153 | 0 | 0 | 0 | 0 | 42153 | [6 empty] | 42154 | 21-02-2023 IFT/IFT23052015627/RIUP22/2241/GURU NANAK ENGINEE 42154.00
54175
53868 | Rampur Village Drilling work | 2023-01-06 | 21 | 258811 | 34165.8 | 224645.2 | 40436.136 | 265081.336 | 2246.452 | 11232.26 | 81 | 40436.136 | 211085.488 | [6 empty] | 211086 | 18-01-2023 IFT/IFT23018003654/RIUP22/1875/GURU NANAK ENGINEE ₹ 2,11,086.00 | -0.512
53868 | GST release note | 2023-02-20 | 21 | 40436 | 0 | 40436 | 0 | 40436 | 0 | 0 | 0 | 0 | 40436 | [6 empty] | 40436 | 21-02-2023 IFT/IFT23052015626/RIUP22/2242/GURU NANAK ENGINEE 40436.00
53868
53663 | Mohideenpur Village Drilling work | 2023-01-06 | 23 | 248230.5 | 24276 | 223955 | 40312 | 264267 | 2240 | 11198 | 40312 | 2596 | 207921 | [6 empty] | 207921 | 23-01-2023 IFT/IFT23023021724/RIUP22/1925/GURU NANAK ENGINEE ₹ 2,07,921.00 | 0
53663 | GST Release Note | 2023-02-18 | 23 | 40312 | 0 | 40312 | 0 | 40312 | 0 | 0 | 0 |  | 40312 | [6 empty] | 40312 | 27-02-2023 IFT/IFT23058023959/RIUP22/2244/GURU NANAK ENGINEE 40312.00
53663
53627 | Abdulpur Village Drilling work | 2023-01-06 | 22 | 272289 | 30119.85 | 242169.15 | 43590.447 | 285759.597 | 2421.6915 | 12108.4575 | 0 | 43590.447 | 227639.001 | [6 empty] | 227640 | 18-01-2023 IFT/IFT23018003652/RIUP22/1873/GURU NANAK ENGINEE ₹ 2,27,640.00 | -0.999
53627 | GST Release Note | 2023-02-18 | 22 | 43590 | 0 | 43590 | 0 | 43590 | 0 | 0 | 0 | 0 | 43590 | [6 empty] | 43590 | 27-02-2023 IFT/IFT23058023958/RIUP22/2243/GURU NANAK ENGINEE 43590.00
53627
53320 | Buwara Kalan Village Drilling work | 2022-12-12 | 18 | 256348 | 24276 | 232072 | 41773 | 273845 | 2321 | 11604 | 41773 | 0 | 218147 | [6 empty] | 218147 | 20-12-2022 IFT/IFT22354025833/RIUP22/1564/GURUNANAK ENGINEE 218147.00 | 0
53320 | GST release Note | 2023-02-18 | 18 | 41773 | 0 | 41773 | 0 | 41773 | 0 | 0 | 0 |  | 41773 | [6 empty] | 41773 | 27-02-2023 IFT/IFT23058023955/RIUP22/2239/GURU NANAK ENGINEE 41773.00
53320 | [20 empty] | 27-09-2023 IFT/IFT23270029216/RIUP23/2343/GURU NANAK ENGINEE 247500.00 | Advance recovered in Shamli 60724
53279 | Jaitpur Village Drilling work | 2022-12-12 | 19 | 242135 | 35065 | 207070 | 37273 | 244343 | 2071 | 10354 | 37273 | 10537 | 184108 | [6 empty] | 184108 | 07-01-2023 IFT/IFT23007044362/RIUP22/1804/GURU NANAK ENGINEE 184108.00 | 0
53279 | GST Release Note | 2023-02-18 | 19 | 37273 | 0 | 37273 | 0 | 37273 | 0 | 0 | 0 |  | 37273 | [6 empty] | 37273 | 27-02-2023 IFT/IFT23058023957/RIUP22/2240/GURU NANAK ENGINEE 37273.00
53279
53277 | Athai Village Drilling work | 2022-12-12 | 17 | 269731.5 | 40909 | 228823 | 41188 | 270011 | 2288 | 11441 | 41188 | 0 | 215094 | [6 empty] | 215094 | 20-12-2022 IFT/IFT22354025832/RIUP22/1563/GURUNANAK ENGINEE 215093.00 | 0
53277 | GST Release Note | 2023-02-20 | 17 | 41188 | 0 | 41188 | 0 | 41188 | 0 | 0 | 0 |  | 41188 | [6 empty] | 41188 | 23-02-2023 IFT/IFT23054026321/RIUP22/2238/GURUNANAK ENGINEE 41188.00
53277
53100 | Saidpur Village Drilling work | 2022-12-12 | 16 | 246926 | 37633 | 209293 | 37673 | 246966 | 2093 | 10465 | 37673 | 0 | 196735 | [6 empty] | 196735 | 19-12-2022 IFT/IFT22353020422/RIUP22/1560/GURU NANAK ENGINEE ₹ 1,96,355.00 | 0
53100 | GST Release Note | 2023-02-18 | 16 | 37673 | 0 | 37673 | 0 | 37673 | 0 | 0 | 0 |  | 37673 | [6 empty] | 37673 | 27-02-2023 IFT/IFT23058055537/RIUP22/2237/GURU NANAK ENGINEE 37673.00
53100
53098 | Nirgaji Village Drilling work | 2022-11-29 | 14 | 263498 | 39111 | 224387 | 40390 | 264777 | 2244 | 11219 | 40390 | 0 | 210924 | [6 empty] | 210924 | 06-12-2022 IFT/IFT22340028529/RIUP22/1410/GURU NANAK ENGINEE 210924.00 | 0
53098 | GST Release Note | 2023-01-03 | 14 | 40390 | 0 | 40390 | 0 | 40390 | 0 | 0 | 0 |  | 40390 | [6 empty] | 40390 | 03-01-2023 IFT/IFT23003042423/RIUP22/1764/GURU NANAK ENGINEE 40390.00
53098
52732 | Nirdhana Village Drilling work | 2022-11-29 | 15 | 273064.5 | 40460 | 232605 | 41869 | 274474 | 2326 | 11630 | 41869 | 395 | 218254 | [6 empty] | 218254 | 06-12-2022 IFT/IFT22340028528/RIUP22/1411/GURU NANAK ENGINEE 218254.00 | 0
52732 | GST Release Note | 2023-01-02 | 15 | 41869 | 0 | 41869 | 0 | 41869 | 0 | 0 | 0 |  | 41869 | [6 empty] | 41869 | 03-01-2023 IFT/IFT23003042424/RIUP22/1765/GURU NANAK ENGINEE 41869.00
52732
52589 | Sandhawali Village Drilling work | 2022-10-22 | 11 | 273607.5 | 38931 | 234676 | 42242 | 276918 | 2347 | 11734 | 42242 | 1389 | 219206 | [6 empty] | 219206 | 14-11-2022 IFT/IFT22318014480/RIUP22/1236/GURUNANAK ENGINEE 219206.00 | 0
52589 | GST Release Note | 2023-01-02 | 11 | 42242 | 0 | 42242 | 0 | 42242 | 0 | 0 | 0 |  | 42242 | [6 empty] | 42242 | 03-01-2023 IFT/IFT23003042420/RIUP22/1761/GURU NANAK ENGINEE 42242.00
52589
52588 | Bahpur Village Drilling work | 2022-10-22 | 12 | 234194 | 41359 | 192835 | 34710 | 227545 | 1928 | 9642 | 34710 | 1298 | 179967 | [6 empty] | 179967 | 14-11-2022 IFT/IFT22318014479/RIUP22/1235/GURU NANAK ENGINEE 179967.00 | 0
52588 | GST Release Note | 2023-01-02 | 12 | 34710 | 0 | 34710 | 0 | 34710 | 0 | 0 | 0 |  | 34710 | [6 empty] | 34710 | 03-01-2023 IFT/IFT23003042421/RIUP22/1762/GURU NANAK ENGINEE 34710.00
52588
52587 | Badkali Village Drilling work | 2022-10-03 | 7 | 270487.5 | 19330.65 | 251157 | 45208 | 296365 | 2512 | 12558 | 0 | 45208 | 236087 | [6 empty] | 236087 | 12-10-2022 IFT/IFT22285026935/RIUP22/943/GURU NANAK ENGINEER 236087.00 | 0
52587 | GST release Note | 2023-01-03 | 7 | 45208 | 0 | 45208 | 0 | 45208 | 0 | 0 |  | 0 | 45208 | [6 empty] | 45208 | 03-01-2023 IFT/IFT23003042416/RIUP22/1757/GURU NANAK ENGINEE 45208.00
52587
52586 | Pachenda Khurd Village Drilling work | 2022-10-03 | 9 | 259210 | 7192.8 | 252017.2 | 45363 | 297380 | 2520 | 12601 | 0 | 45363 | 236896 | [6 empty] | 236896 | 12-10-2022 IFT/IFT22285026934/RIUP22/942/GURU NANAK ENGINEER 236896.00 | 0
52586 | GST release Note | 2023-01-02 | 9 | 45363 | 0 | 45363 | 0 | 45363 | 0 | 0 |  | 0 | 45363 | [6 empty] | 45363 | 03-01-2023 IFT/IFT23003042418/RIUP22/1759/GURU NANAK ENGINEE 45363.00
52586
52585 | Badhai Khurd Village Drilling work | 2022-10-03 | 8 | 251703.5 | 36413.55 | 215290 | 38752 | 254042 | 2153 | 10765 | 0 | 38752 | 202372 | [6 empty] | 202372 | 12-10-2022 IFT/IFT22285026933/RIUP22/935/GURU NANAK ENGINEER 202373.00 | 0
52585 | GST Pay | 2023-01-03 | 8 | 38752 | 0 | 38752 | 0 | 38752 | 0 | 0 |  | 0 | 38752 | [6 empty] | 38752 | 03-01-2023 IFT/IFT23003042417/RIUP22/1758/GURU NANAK ENGINEE 38752.00
52585
52396 | Manganpur Village Drilling work | 2022-11-08 | 13 | 264268 | 30569 | 233699 | 42066 | 275765 | 2337 | 11685 | 42066 | 0 | 219677 | [6 empty] | 219676 | 22-11-2022 IFT/IFT22326006432/RIUP22/1318/GURU NANAK ENGINEE 219676.0 | 1
52396 | GST Release Note | 2023-01-03 | 13 | 42066 | 0 | 42066 | 0 | 42066 | 0 | 0 | 0 |  | 42066 | [6 empty] | 42066 | 03-01-2023 IFT/IFT23003042422/RIUP22/1763/GURU NANAK ENGINEE 42066.00
52396
52263 | Pachenda Kalan Village Drilling work | 2022-10-22 | 10 | 271840.5 | 35514.45 | 236326 | 42539 | 278865 | 2363 | 11816 | 42539 |  | 222147 | [6 empty] | 222147 | 10-11-2022 IFT/IFT22314019267/RIUP22/1213/GURU NANAK ENGINEE 222147.00 | 0
52263 | GST Release Note | 2023-01-03 | 10 | 42539 | 0 | 42539 | 0 | 42539 | 0 | 0 | 0 |  | 42539 | [6 empty] | 42539 | 03-01-2023 IFT/IFT23003042419/RIUP22/1760/GURU NANAK ENGINEE 42539.00
52263
51699 | Bibipur Village Drilling work | 2022-08-06 | 6 | 265775 | 42257.7 | 223517.3 | 40233 | 263750.3 | 2235 | 11176 | 645 | 40233 | 209461 |  |  | 0 | 0 | 0 |  | 209461 | 03-09-2022 IFT/IFT22246004289/RIUP22/639/GURU NANAK ENGINEER 209461.00 | 0
51699 | GST Release Note | 2023-01-03 | 6 | 40233 | 0 | 40233 | 0 | 40233 | 0 | 0 |  | 0 | 40233 | [6 empty] | 40233 | 03-01-2023 IFT/IFT23003042425/RIUP22/1766/GURU NANAK ENGINEE 40233.00
51699
51597 | Datiyana Village Drilling work | 2022-07-19 | 4 | 273195 | 33266.7 | 239928.3 | 43187.094 | 283115.394 | 2399.283 | 11996.415 | 43187.094 | 3918.4382 | 221614.1638 | [6 empty] | 221614 | 22-08-2022 IFT/IFT22234021090/RIUP/573/GURU NANAK ENGINEERS 221615.00 | 0.16376
51597 | GST Release Note | 2022-08-20 | 4 | 43187 | 0 | 43187 | 0 | 43187 | 0 | 0 | 0 |  | 43187 | [6 empty] | 43187 | 22-08-2022 IFT/IFT22234020180/RIUP/574/GURU NANAK ENGINEERS 43187.00
51597
51411 | Raee Village Drilling work | 2022-07-18 | 3 | 230796 | 0 | 230796 | 41543 | 272339 | 2308 | 11540 | 41543 | 0 | 216948 | [6 empty] | 216948 | 09-08-2022 IFT/IFT22221010019/RIUP22/422/GURU NANAK ENGINEER 216948.00 | 0
51411 | GST Release Note | 2022-07-18 | 3 | 41543 | [8 empty] | 41543 | [6 empty] | 41543 | 24-08-2022 IFT/IFT22236053362/RIUP22/564/GURU NANAK ENGINEER 41543.00
51411
51336 | Parai Village Drilling work | 2022-07-22 | 5 | 263477 | 35064.9 | 228412.1 | 41114.178 | 269526.278 | 2284.121 | 11420.605 | 41114.178 | 0 | 214707.374 | [6 empty] | 214707 | 28-07-2022 IFT/IFT22209041365/RIUP22/421/GURUNANAK ENGINEER 214707.00 | 0.374
51336 | GST Release Note | 2022-08-20 | 5 | 41114 | 0 | 41114 | 0 | 41114 | 0 | 0 | 0 |  | 41114 | [6 empty] | 41114 | 24-08-2022 IFT/IFT22236053363/RIUP22/563/GURUNANAK ENGINEER 41114.00
51179 | Kasauli Village Drilling work | 2023-04-06 | 1 | 248981 | 0 | 248981 | 44817 | 293798 | 2490 | 12449 | 44817 | 0 | 234042 | [6 empty] | 234042 | 05-07-2022 IFT/IFT22186018973/RIUP22/293/GURU NANAK ENGINEER 234042.00 | 0
51179 | GST Release Note | 2022-08-20 | 1 | 44817 | [8 empty] | 44817 | [6 empty] | 44817 | 22-08-2022 IFT/IFT22234020181/RIUP/565/GURU NANAK ENGINEERS 44817.00
51179
51162 | Kasauli Village Drilling work | 2022-06-08 | 1 | 234116 | 0 | 234116 | 42141 | 276257 | 2341 | 11706 | 42141 | 0 | 220069 | [6 empty] | 220069 | 16-06-2022 IFT/IFT22167019537/RIUP22/200/GURUNANAK ENGINEER 220069.00 | 0
51162 | GST Release Note |  | 1 | 42141 | [8 empty] | 42141 | [6 empty] | 42141 | 22-08-2022 IFT/IFT22234020182/RIUP/566/GURU NANAK ENGINEERS 42141.00
51162
51162
[10 empty] | 333513.1175 | 875832.272 | 352261.8292 | 7443139.3708 |  |  |  | Total Paid Amount Rs. - |  |  | 7443139 |  | 0.37076
[17 empty] | Balance Payable Amount Rs. - |  |  | 0.37076
M/S Gurunanak Engineers
2024-12-24
[8 empty] | Total Hold ( SD+OC+HT ) |  | 333513.1175
[8 empty] | DPR Excess Hold |  | 352261.8292
[8 empty] | Advance / Surplus |  | 0.37076
Debit
[8 empty] | GST Remaining |  | 0